## Cognos Reports - at Go-Live
Module | Report Name | UCD Report ID | UCPATH Report ID | Report Intent | Report Parameters | Business Need / Intended Audience | When Will Report Be Run | Status | Notes
Absence Management | Leave Accrual and Balances Summary Report | UCP-022 | R-022 | The report is used by the locations to know details of accrual hours of employees. This is needed by supervisors and unit/department heads to monitor balances. | - Business Unit - Department - Employee Class - HR Status - Payroll Status - As of Date - Union Code - Leave Type | Supervisors and Unit Heads. | Report should be run ad-hoc as needed. | Needs to be developed
Absence Management | Leave Accruals Summary Report | UCP-372 | R-372 | This report shows the leave accruals by employee. | - Pay Period End Date - Business Unit - Department | Supervisors and Unit Heads. | Report should be run ad-hoc as needed. | In Cognos DEV, awaiting additional user input
Absence Management | Leave Accrual Tier Movement Report | UCP-373 | R-373 | This report is to capture employees’ total service months to determine if the leave accruals are updated appropriately for each employee based on the Years of Qualifying Service tiers. | - Pay Period End Date - Business Unit | Supervisors and Unit Heads. | Report should be run ad-hoc as needed. | In Cognos DEV, awaiting additional user input
Benefits | Identify EE on Leave for More Than 6 Months | UCP-374 | R-374 | This report is developed to capture employees who are on Leave without Pay (LOA) for more than 6 months. | - Business Unit - Department |  | Report should be run ad-hoc as needed. | In Cognos DEV, awaiting additional user input
Compensation | MCOP Report | UCP-045 | NA | The purpose of this report is to provide compensation information, including multiple components of pay. | - Comp Effective Date - Employee Status - Employee Class - Sal Admin Plan - Grade - Search by Roll-Up Department - Search by Department - Search by Employee - Search by Comp Rate Code - Search by BUSINESS UNIT | MCOP Report break an employee’s pay into different components for reporting and/or budgeting purposes. MCOP report provide the ability to track different types of pay for an employee on a single employee record number. | Report should be run ad-hoc as needed. | Testing
Compensation | Job Code Review Table Report | UCP-349 | R-349 | Manage the Job Code, Salary Administration, Salary Grade, Job Function, Job Family, Union Code, Empl Class, Salary Steps. UCOP –HR Department will need to assure the integrity and accuracy of these tables. | (No Filters)
Compensation | Employee Performance Rating Report | UCP-352 | R-352 | Locations need this report to monitor employee performance rating details. Manage the Job Code, Salary Administration, Salary Grade, Job Function, Job Family, Union Code, Empl Class, Salary Steps. UCOP –HR Department will need to assure the integrity and accuracy of these tables. | - Business Unit (Required) - Department ID - FROM DATE (REQUIRED) |  | Report should be run ad-hoc as needed.
GL Integration | Budget Costing Report | UCP-125 | R-125 | Budget Costing Report pulls detailed data of employee change in compensation and Compensation Change Information includes Job and Position related elements. E-718 would capture and report compensation changes for permanently budgeted employees. | - SETID - From/To Date - Dept Id - Union Code - Employee Class - Position Number | Locations want to monitor the details of compensation changes occurred in employee’s job data with their accounting information. This will help locations to review the budget costing information. | This query will be run ad-hoc by any business owner and will not be included as part of the nightly batch process. | Waiting for user input
GL Integration | e-Verify Needed (Funding) Report |  | R-381 | The purpose of this report is to list instances where an employee has funding set up in Commitment Accounting that uses an e-Verify fund, but the employee has not been e-verified. | - SETID - Fiscal Year - Department | - UCPC will use this report to monitor occurrences and if locations do not clean these occurrences up will reach out to them directly. - Locations will use this report to work to get the employee e-verified or move them off of the e-verify fund. | This query will be run ad-hoc by any business owner and will not be included as part of the nightly batch process.
GL Integration | Graduate Student Title Expense Report |  | PPS-189 | [5 empty] | Can this be satisfied by the UCP-339 report?
GL Integration | Fee Remission Report |  | PPS-238
GL Integration | Staffing List |  | PPS-37/PPS34 | [5 empty] | Aggie Budget was supposed to create this… might need to produce it.
GL Integration | Work Study Award Balance | UCP-208 | R-208 | This report is to monitor for work study employees whose award balance amount is approaching a user-defined amount (e.g. zero (0) dollars). | - SETID - Work Study Academic Year - Award Balance - Employee ID - Session Code - Position Pool ID | Location users will use this report to find that students are approaching a 0 dollar award balance. | This report can be run ad-hoc after every pay period after work study table gets updated by the custom E-716 process. | Testing
GL Integration | 339 Payroll Expense Distribution | UCP-339 | NA | The Payroll Expense Distribution report is used to view detail payroll actuals information. Users can use the report to review and analyze detail payroll transactions as well as use the paycheck number, and fringe benefit information for cost transfers. The Cognos Payroll Expense Distribution Report will utilize extensive filter prompts which will allow the user to limit results, define data fields returned, and determine report layout. The report will display labor ledger data in both detail and summary views. | - Fiscial Period - Employee Class - Chart - Pay Period End Date - Bargaining Unit - Earn Code - Job Code - Employee - HR Department - Organization - Fund - Account |  | This report can be run ad-hoc | Development | New report from KFS requested by GL module leads.
Payroll | Local Deduction Remittance Report | UCP-139 | R-139 | This report is an all-encompassing report that includes payroll deductions (e.g. general deductions, benefits deductions, and garnishments) withheld from employee paychecks for each pay cycle. |  | As part of AP Voucher Processing, locations will use this report to identify the appropriate method of payment for all the deductions if they are responsible for the vendor payment. | Run after each pay period confirmation completed successfully. Bi-weekly/Monthly | In Cognos DEV, awaiting additional user input
Payroll | Employee Record of Earnings Detail Report | UCP-270 | R-270 | This report will show the earning details for all the employees for the deduction line descriptions not in: • 'GAEL EL Assessment - Liability', • 'GAEL GL Assessment - Liability', • 'InterBU Liability - Campus', • 'Vacation Taken', • 'InterBU Liability - UCPC', • 'Leave Assessment - Liability' • 'UCOP COMBO CODE' | - Comp Effective Date - To Date - Pay End Date - Business Unit - FS Dept - Employee ID |  | Report should be run ad-hoc as needed. | Waiting for user input
Payroll | Employees total hours (sick, vacation, hours worked) | UCP-366 | R-366 | This report will be as a reconciliation tool to monitor employee’s accrual balances. | - Business Unit - Department - As of Date | This report will be used by Locations and UCPath Center AM team as reconciliation tool and audit employees accrual balances. | This report is scheduled to run after every pay cycle (bi-weekly & monthly). It also can be run ad-hoc. | In Cognos DEV, awaiting additional user input
UCDH | Department Roster Report | UCP-001 | NA | The Department Roster report page is the primary resource used to verify and validate departmental employee information such as: job code, title, positon, FTE, union, class, rate, step, hire date, account code, etc. | - Set ID - Depatment ID | UC Davis Health currently uses the Department Roster online report to support a variety of operational activities. | Report should be run ad-hoc as needed. | Testing
UCDH | Employee Locator report | UCP-002 | NA | UC Davis Health currently use the Employee Locator online report to support a variety of operational activities. The Employee Locator is the primary resource used to verify and validate employee position, location, report to relationship and department assignment. | - Employee ID - Employee Name | UC Davis Health currently use the Employee Locator online report to support a variety of operational activities. | Report should be run ad-hoc as needed. | Testing
UCDH | Position Control Report | UCP-003 | NA | The Position Control report page is the primary resource used to verify and validate departmental employee position information such as: position, job code, job title, employee classification, FTE, hire date, termination date, ALT home, reports to, supervisor name, etc. | - Set ID - Depatment ID | UC Davis Health currently uses the Position Control online report to support a variety of operational activities. | Report should be run ad-hoc as needed. | Testing, still a few data items missing because we cannot identify. Filled FTE and Vacant FTE.
UCDH | Terminations Report | UCP-004 | NA | This report contains employee termination information.This report will include the following termination information: Employee ID, Last Name, First Name | (Requested as an automated extract) | UC Davis Health |  | Development
UCDH | Transfers Report | UCP-005 | NA | This report contains transfer information for current employees. This report will include the following employee transfer information : Employee ID, Last Name, First Name, Transfer Date, New Department, Old Department | (Requested as an automated extract) | UC Davis Health |  | Development
UCDH | FIS View | UCP-006 | NA | Provide the capacity of producing a view of the UCDH Data Mart which shows faculty information. This view will include the following faculty information. First Name, Last Name, Employee ID, Employee Record Number, Effective Date, Department ID, Job Code, Job Description | (Requested as an automated extract) | UCDH Controller uses data provided for this report to validate employee status (e.g., active, inactive, etc.) and position to update purchasing authorization. |  | Development
UCDH | Daily Hire Report | UCP-007 | NA | Provide the capability of producing a Business Intelligence (BI) report which contains daily employee hire information. This report is called the Daily Hire Report. This report will include the following employee information: First Name, Last Name, ID (UCPath Empl-ID), Hire Date, Job Code, Job Description, Salary Plan, Salary Grade, Workers Comp Code, Department ID, Department Name, Supervisor Name, Class | (Requested as an automated extract) | UCDH Controller uses data provided for this report to validate employee status (e.g., active, inactive, etc.) and position to update purchasing authorization. |  | Development
UCDH | Employee Extract Report | UCP-008 | NA | Provide the capability of producing a Business Intelligence (BI) report which contains all of the daily employee hire information for the previous quarter. This report is called the Employee Extract Report. This report will include the following employee information: First Name, Last Name, Employee ID, Job Code, Job Description, Salary Plan, Salary Grade, Workers Comp Code, Department ID, Department Name, Supervisor Name, Employee Class | (Requested as an automated extract) | UCDH Controller uses data provided for this report to validate employee status (e.g., active, inactive, etc.) and position to update purchasing authorization. |  | Development
Workforce Administration | Jobs with Approaching End Dates Report | UCP-103 | R-103 | This report is used to identify those employees whose job records have end dates 30/60 calendar days out from the date the report is run. | - Business Unit - HR Department - Employee Class - Reports to Position Number | Locations will use this dataset to determine if end dates are required to change | This report can be run ad-hoc at any time and does not require any processes to run prior. | Waiting for user input
Workforce Administration | Benefits Eligibility | UCP-150 | R-150 | The purpose of these reports is to find newly eligible academic (faculty and non-faculty) employees who have reached/approaching 750/1000 hours within a rolling twelve months period. | - Business Unit - As-of Date - Department | UCPC/Locations want to identify employees who have completed 750/1000 hours and who are approaching 750/1000 hours in certain circumstances, within a rolling twelve months period. UCPC/Locations need two reports to identify: - Applicable to Unit 18 Lecturers who are in AFT bargaining Unit (IX unit) who have completed 750 hours. - Applicable for all employees excluding students/post docs who have completed 1000 hours. UCPC/Locations need two reports to identify: - Applicable to Unit 18 Lecturers who are in AFT bargaining Unit (IX unit) who have completed hours in between 670 and 750 hours. - Applicable for all employees excluding students/post docs who have completed hours in between 920 and 1000 hours. | This report can be run ad-hoc at any time and does not require any processes to run prior. | Waiting for user input
Workforce Administration | AA New Appointment Hires | UCP-191 | R-191 | This report will help locations to supply with the appropriate information in order to review affirmative action plan data. This requirement will provide new appointments/Hires information. | - Business Unit - Department - Effective Date - Employee Class | These reports are regulatory in nature so accurate information is needed to report to the government agencies and take an appropriate action with the real time data. |  | Needs to be developed
Workforce Administration | Employee Roster Report | UCP-272 | R-272 | This report will pull data for employees whose Termination date or expected end date is greater than a specified date. | - Termination Date - Business Unit - Department | Locations will run this report to find academic and non-academic employees whose Termination date or Expected End date is greater than a defined date. | The job will run on a daily basis and the report should be sent to central office at LAMED BU and LACMP BU only. | In Cognos DEV, awaiting additional user input
Workforce Administration | Personnel Status Report | UCP-302 | R-302 | Personnel Status Report is needed for a variety of WFA purposes, including monitoring of New hires and separations, salary review periods, an Appointment changes. | - Business Unit - From/To Date - Department | The business purpose is to create new report for a variety of Work Force Administration purposes allowing locations/UCPC to manage their employees and related job data integrity, taking necessary actions to mitigate the risk of data errors, and implementing key controls at their location. | Report should be run ad-hoc as needed. | Waiting for user input
Workforce Administration | I-156 FICA Exempt Inbound Student Status audit report | UCP-326 | R-326 | This report identifies which Employees that had FICA updated not based on what is in Job but based on this Student Profile override. | - Business Unit - Run ID | Locations need to monitor the details of employees who have the student status manually overridden at the student employee profile level within the pay period begin and pay period end date. | This report can be run at user discretion at any time. | Waiting for user input
Workforce Administration | Student FICA Audit Report on Job Data | UCP-327 | R-327 | This report will show employees who have a change in their FICA status on their Job data in between pay begin and pay end date based on run id entered on the run control. Report also captures if FICA status changes occurs in correction mode, report will look between the action date ranges entered on the run control page. | - Run ID - Action Date | Student employees are exempt from FICA taxes if enrolled in a minimum number of class credits. This report indicates the active student employees who do not meet the minimum units required per semester or quarter to be eligible for student jobs. | This report can run right after I156 process run or prior to each payroll run. | Waiting for user input
Workforce Administration | Crosscheck Employees in PPS and PS | UCP-347 | R-347 | This report will produce a list of employees with their PPS ID and PeopleSoft Employee ID. Labor Relations will directly use this dataset to then send the applicable data to the correct unions. | - Business Unit - Department - Sub Division - Division | The report will exist for any ad-hoc needs of requiring the cross-walk of PPS ID to PeopleSoft EmplID. | This report will be run at the time of conversion for each Location’s go-live. | In Cognos DEV, awaiting additional user input
Workforce Administration | Auto Terminated Employees | UCP-354 | R-354 | This report generates a list of employees who were terminated by the Auto Termination nightly process. | - Business Unit - Department - Effective Date | This report is used by UCPC WFA team to audit employees who were terminated by the auto-termination process | This will be run ad-hoc to reconcile the other reports that are run prior to the termination of these employees. | Development
Workforce Administration | Vacation Accrual Report | UCP-364 | R-364 | This report provides the paper pay check for the employees with unions reaching 80% of their allowed vacation. | - Business Unit - Pay End Date - Union Code | The report is used by the locations to know the paper pay check information for the employees with unions reaching 80% of their allowed vacation. | Report should be run ad-hoc as needed. | Waiting for user input
Workforce Administration | Employee Service Credits Report | UCP-370 | R-370 | This report provides the order service awards for employees. | - Pay Period End Date - Set ID - Dept | The report is used by the locations to track employees who will be reaching a service milestone and to order service awards for the employees. | Report should be run ad-hoc as needed. | In Cognos DEV, awaiting additional user input
Workforce Administration | Concurrent Jobs Report | UCP-379 | R-379 | The purpose of this report is to to identify employees within a Business Unit and Department with concurrent jobs and total FTE>1.0 | (No Filters) | In order to ensure employees who have two ro more jobs do not exceed a total percent time of 100% for all jobs, this query is needed to capture employees who exceed the 100% time employment and don’t have a dual employment. | Report should be run ad-hoc as needed. | Waiting for user input
Workforce Administration | Hours Toward Career Status Report | UCP-380 | R-380 | Employees with 1,000 toward career status and employees approaching 1,000 hours toward career status within a 12 month period. | - HR Status - Business Unit - Dept - As of Date - Employee Id | To track 'Limited' employee hours per PPSM-3. When a 'Limited' employee has reached a 1,000 qualifying hours, they will be converted to Career status. | Report should be run ad-hoc as needed. | Waiting for user input
Workforce Administration | Work Authorization Expiration Report for Non-Residents | UCP-382 | R-382 | This report captures the expiration dates of non-residents’ work authorization documentation for Locations to complete re-verification of I-9 process. | - Business Unit - Department | WFA team needed the report to monitor the expiration dates for I-9 documentation for non-residents aliens and ensures that we are compliant with regulations regarding work authorization. | WFA team to run ad-hoc at will. | Waiting for user input

## Cognos Reports - post Go-Live
Module | Report Name | Report Intent | Report Parameters | Business Need / Intended Audience | When Will Report Be Run | Status | Notes
?? | Staff Incentive Plan |  |  |  |  | UCI developed - UCDH (Bill Gregory requesting)
?? | Clinical Incentive report |  |  |  |  | UCI developed - UCDH (Bill Gregory requesting)
?? | Name Change Report | For Personal Data Changes WFA.10, will there be a Name Change report available to location for use in updating ancillary systems? |  |  |  | Owner - Jacob Miller Assignee - Michelle Wong Requested on Wednesday, November 26, 2018
?? | License expiration report | Request that UCPath Team explore level of automation in report of upcoming expirations for WFA.64L Licensure & Certification Re-verification |  |  |  | Owner - Jacob Miller Assignee - Michelle Wong Requested on Wednesday, November 28, 2018
WFA | R-191 New Appointments /Hires | UC Human Resources bolsters Equal Employment Opportunity/Affirmative Action Plan (EEO/AAP) announcing prerequisites by empowering you to characterize occupations and positions filled by candidates and workers in particular sexual orientation and ethnic gatherings. Utilize this data to characterize governmental policy regarding minorities in society objectives and timetables and produce the important government reports. |  | This report will help locations to supply with the appropriate information in order to review affirmative action plan data. This requirement will provide new appointments/Hires information. These reports are regulatory in nature so accurate information is needed to report to the government agencies and take an appropriate action with the real time data.
Payroll | GTN Report |  |  | When entering General Deductions, there is no approval process. A report to identify General Deductions entered into the system with a date range would be awesome. |  |  | (New Report Request by Kelly Davidson)
?? | Report to look up transaction status in UCPath |  |  | Currently there is NO central way to look up transaction status in UCPath. If there was some sort of report where people could put in their user ID (or maybe other variables) to track where/what the status of transactions are would be amazing! |  |  | (New Report Request by Kelly Davidson)
Payroll | PPS DS58 - Total Population (Headcount Rpt) | [5 empty] | Requsted by Theresa Schumacher
GL | PPS DS 144 – PPP6406 – Leave Liability by Chart/FC | [5 empty] | Requsted by Theresa Schumacher